## Sheet1
Software Engineering and Systems Development
Group 40
| Task Name | Semester 1 | [8 empty] | Semester 2
|  | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-01-11 | 2020-01-18 | 2020-01-25 | 2020-02-01 | 2020-02-08 | 2020-02-15 | 2020-02-22 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22
|  | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11
1 | Back From the Brink
2 | The Problem and the Early Solution | bar: Wk3 to Wk11
3 | Use Case Requirements Specification and Planning | bar: Wk3 to Wk5
4 | Gantt Chart | bar: Wk3
5 | Use Case Diagram | bar: Wk4 to Wk5
6 | Use Case Decsription | bar: Wk4 to Wk5
7 | System Analysis | bar: Wk6 to Wk9
8 | Class Diagram | bar: Wk6 to Wk8
9 | Use Case Realisation | bar: Wk6 to Wk8
10 | Draft Game Layout | bar: Wk9
11 | Interim Demo | bar: Wk10
12 | Peer Assessment | bar: Wk11
13 | Problem & Early Solution | bar: Wk11
14 | PDF Report | bar: Wk3 to Wk11
15 | The System, the Final PDF Report, and the Process | bar: Wk1 to Wk11
16 | The Working System | bar: Wk1 to Wk4
17 | Basic Functionality | bar: Wk1 to Wk3
18 | Value Added Features | bar: Wk3 to Wk4
19 | Design Documentation | bar: Wk5 to Wk7
20 | Text User Interface | bar: Wk5 to Wk7
21 | Class Relationship Model &Sequence Diagrams | bar: Wk5 to Wk7
22 | Final Game Layout | bar: Wk7
23 | Implementations related documentations | bar: Wk8
24 | A Test Plan | bar: Wk8
25 | Adherence to Process | bar: Wk9 to Wk10
26 | Peer Assessment | bar: Wk10 to Wk11
27 | System | bar: Wk10 to Wk11
28 | Final PDF Report | bar: Wk10 to Wk11
29 | Process | bar: Wk10 to Wk11